## Sheet1
Santo Rae & Nicholas Holmes
n12029408 & n12017035
Week 09 | 2025-09-15
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Santo | Start Creating Index UI page | Medium | coding started | In Progress
2 | Nicholas | Researching Project Layout | High | ongoing | In Progress
3 | Nicholas | Create models for application | Medium | coding started | In Progress
4 | Santo | Researching Bootstrap Classes and Structure | High | ongoing | In Progress
Week 10 | 2025-09-29
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Nicholas | Finsih off creating classes | High | completed | Completed
2 | Nicholas | Get database initialised and setup in the project | Medium | researching | In Progress
3 | Santo | Start creation of quotation requests UI for customer | Medium | coding started | In Progress
4 | Santo | Complete index ui page | High | completed | Completed
Week 11 | 2025-10-06
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Santo
2 | Nicholas
3 | Santo
4 | Nicholas
Week 12 | 2025-10-13
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Santo
2 | Santo
3 | Nicholas
4 | Nicholas
Week 13 | 2025-10-20
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Santo
2 | Nicholas
3 | Nicholas
4 | Santo
Week 14 | 2025-10-27
NO. | ASSIGNED TO | PRIORITIES | PRIORITY LEVEL | PROGRESS | PROGRESS STATUS | PROBLEMS AND COMMENTS
1 | Nicholas
2 | Santo
3 | Santo
4 | Nicholas